## source
https://www.researchgate.net/publication/215576638_Interim_Report_The_Analysis_of_Microarray_Data_DEMO

## original
id | priority | details | status | deadline | completed | project
number | integer | text | text | date | date
new, pending, done, canceled
100 | 1 | Deliverable: Literature Review Document | done | 2011-06-06 | 2011-06-06 | 100
200 | 1 | Deliverable: Software Infrastructure (MATLAB) | done | 2011-06-06 | 2011-06-06 | 200
300 | 1 | Deliverable: Microarray Data Sets | done | 2011-06-06 | 2011-06-13 | 300
400 | 1 | Data Set 1: Stanford University Yeast Cell-Cycle Data Set Analysis | done | 2011-07-25 | 2011-08-01 | 400
419 | 1 | Initial Analysis | done | 2011-06-13 | 2011-06-13 | 400
410 | 1 | Clustering Method Implementation | new | 2011-06-20 | 2011-06-20 | 400
429 | 3 | Machine Learning Methods Design & Implementation | canceled | 2011-06-27 |  | 400
420 | 1 | Simulation | done | 2011-07-04 | 2011-07-11 | 400
430 | 1 | Results Analysis | done | 2011-07-11 | 2011-07-25 | 400
440 | 2 | New Method Design & Implementation | new | 2011-07-11 | 2011-07-11 | 400
450 | 1 | Concluding | done | 2011-07-16 | 2011-07-25 | 400
460 | 1 | Publication Writing | done | 2011-07-25 | 2011-08-01 | 400
461 | 1 | Deliverable: Publication Document | done | 2011-07-25 | 2011-08-01 | 400
500 | 2 | Interim Report Writing | done | 2011-07-16 | 2011-07-16 | 500
510 | 2 | Progress Assessment and Rescheduling | new | 2011-07-16 | 2011-07-16 | 500
520 | 2 | Deliverable: Interim Report | done | 2011-07-16 | 2011-07-16 | 500
600 | 1 | Data Set 2: Oxford University Data Set | done | 2011-09-12 | 2011-09-12 | 600
619 | 1 | Initial Analysis | done | 2011-07-25 | 2011-07-25 | 600
610 | 1 | Data Analysis for Potential Work Paths | new | 2011-08-08 | 2011-08-08 | 600
629 | 3 | Machine Learning Methods Design & Implementation | canceled | 2011-08-08 |  | 600
620 | 1 | Simulation | done | 2011-08-15 | 2011-08-15 | 600
630 | 1 | Results Analysis | done | 2011-08-22 | 2011-08-29 | 600
640 | 1 | Concluding | done | 2011-08-29 | 2011-09-05 | 600
650 | 1 | Publication Writing | done | 2011-09-12 | 2011-09-19 | 600
651 | 1 | Deliverable: Publication Document | done | 2011-09-12 | 2011-09-19 | 600
700 | 1 | Final Report (Thesis) Writing | done | 2011-09-12 | 2011-09-12 | 700
710 | 1 | Deliverable: Final Report (Thesis) | done | 2011-09-12 | 2011-09-12 | 700
800 | 1 | Presentation Preparation | done | 2011-09-16 | 2011-09-16 | 800
810 | 1 | Presentation Slides | done | 2011-09-16 | 2011-09-16 | 800

## Project
project_id | name | description | deadline
400 | Analysis of Yeast Cell Cycle Data | Analysis of Data Set 1: Stanford University Yeast Cell Cycle Data Set | 2011-07-25
600 | Analysis of Microarray Data | Analysis of Data Set 2: Oxford University Microarray Data Set | 2011-09-12

## Task
task_id | priority | details | status | deadline | completed | project_id
100 | 1 | Deliverable: Literature Review Document | done | 2011-06-06 | 2011-06-06 | 400
200 | 1 | Deliverable: Software Infrastructure (MATLAB) | done | 2011-06-06 | 2011-06-06 | 400
300 | 1 | Deliverable: Microarray Data Sets | done | 2011-06-06 | 2011-06-13 | 400
410 | 1 | Initial Analysis | done | 2011-06-13 | 2011-06-13 | 400
419 | 1 | Clustering Method Implementation | new | 2011-06-20 | 2011-06-20 | 400
420 | 3 | Machine Learning Methods Design & Implementation | canceled | 2011-06-27 |  | 400
429 | 1 | Simulation | done | 2011-07-04 | 2011-07-11 | 400
430 | 1 | Results Analysis | done | 2011-07-11 | 2011-07-25 | 400
440 | 2 | New Method Design & Implementation | new | 2011-07-11 | 2011-07-11 | 400
450 | 1 | Concluding | done | 2011-07-16 | 2011-07-25 | 400
460 | 1 | Publication Writing | done | 2011-07-25 | 2011-08-01 | 400
461 | 1 | Deliverable: Publication Document | done | 2011-07-25 | 2011-08-01 | 400
500 | 1 | Interim Report Writing | done | 2011-07-16 | 2011-07-16 | 400
510 | 1 | Progress Assessment and Rescheduling | new | 2011-07-16 | 2011-07-16 | 400
520 | 1 | Deliverable: Interim Report | done | 2011-07-16 | 2011-07-16 | 400
610 | 1 | Initial Analysis | done | 2011-07-25 | 2011-07-25 | 600
619 | 1 | Data Analysis for Potential Work Paths | new | 2011-08-08 | 2011-08-08 | 600
620 | 3 | Machine Learning Methods Design & Implementation | canceled | 2011-08-08 |  | 600
629 | 1 | Simulation | done | 2011-08-15 | 2011-08-15 | 600
630 | 1 | Results Analysis | done | 2011-08-22 | 2011-08-29 | 600
640 | 1 | Concluding | pending | 2011-08-29 |  | 600
650 | 1 | Publication Writing | pending | 2011-09-12 |  | 600
651 | 1 | Deliverable: Publication Document | pending | 2011-09-12 |  | 600
700 | 1 | Final Report (Thesis) Writing | pending | 2011-09-12 |  | 600
710 | 1 | Deliverable: Final Report (Thesis) | pending | 2011-09-12 |  | 600
800 | 1 | Presentation Preparation | pending | 2011-09-16 |  | 600
810 | 1 | Presentation Slides | pending | 2011-09-16 |  | 600